Section 3 Assignment 4 – Manage Stakeholder Engagement and Risk Register

Manage Stakeholder Engagement

Refer to 13.3 Manage Stakeholder Engagement in the Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) - Sixth Edition, Project Management Institute, Inc., 2017, Pages 523-529.

There are five tools and techniques for manage stakeholder engagement:  expert judgement, communication skills, interpersonal and team skills, ground rules, and meetings.  Describe how you would use these tools and techniques to engage your stakeholders in the management of your project.  You are required to make two selections for this response (e.g., one communication method and one interpersonal skill).

Selection 1:

Communication method: Progress Reporting. At SLSP a progress reporting is essential at any meeting or communication with stakeholders since meetings are difficult to schedule and there are many projects happening at any given time. It’s very helpful for the stakeholders to have a physical documentation of the issue that is being discussed and how it will potentially impact the project.

Selection 2:

Interpersonal Skill: Cultural Awareness. The stakeholders at SLSP come from different backgrounds and are interested in helping a very specific and culturally different segment of the population. For these reasons is very important to explain, in cultural terms, why the project team makes a specific decision regarding the project, such as why is an all-female personnel necessary for Muslim women, or the requirements to choose a neighborhood over another.

PMBOK is a registered mark of the Project Management Institute, Inc.

Risk Register

Refer to 11.2 Identify Risks in the PMBOK® Guide, Pages 409-418.

In considering your project, create a list of three possible risks.  Complete the chart below to describe the risks, the probability of them occurring, the impact of the risks and what your mitigation should be.

| # | Risk Description | Probability(L/M/H) | Impact (L/M/H) | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| 1 | The corona virus pandemic makes a return and Miami is forced into another lockdown halting the project completely. | High | High | The project team can make remote work the norm and have all documents ready online such that if another lockdown happens, the project can still make progress. | Julie Tapia- Operations |
| 2 | The housing market booms after the pandemic making the prices of real state out of budget. | High | High | The project team can talk with the board of directors to increase the budget or delay the project until the demand stabilizes. | Sara Suarez- Project Manager |
| 3 | The vaccines are seen as unsafe and are volunteers refuse to get vaccinated, risking infecting the team and other volunteers. | Medium | High | The marketing department can issue communications sent to volunteers explaining why a vaccine is necessary. Vaccine cards can be required for volunteers to be accepted | Brendon Teles- Marketing. Julie Tapia- Operations. |

L=Low, M=Medium, H=High

PMBOK is a registered mark of the Project Management Institute, Inc.