Section 3 Assignment 5 – Project Charter Update

For the Section 3, Assignment 5, complete the Project Charter that you partially completed in Section 2 Assignment 3.  The Project Charter is a living document and can be revised as new information is available.  Review all of the sections, as you may have new or revised information as the project has progressed.  Each section has instructions for content that should be built out in each template section.  Add your project information to the Project Charter and remove the italicized instructions before submission for grading.

| 1. General Project Information – Update if necessary |  |  |  |
| --- | --- | --- | --- |
| Project Name: | SLSP Miami Charter |  |  |
| Project Description: | Provide a brief description of this project. (Information from the Description from Section 2 Assignment 1 can be incorporated here) |  |  |
| Executive Sponsor(s): | Catalina Suarez (VP of SLSP), John Suarez (CEO of SLSP). |  |  |
| 2. Project Team – This list should be expanded from the Section 2 Assignment |  |  |  |
| #### Name |  | #### Department |  |
| List your name |  | Your department name |  |
| Sara Suarez |  | Project Manager |  |
| Julie Tapia |  | HR VP |  |
| Dunia Tonob |  | Operations Manager |  |
| Brendon Teles |  | Head of Marketing. |  |
| Mike Smith |  | Realtor |  |
| Johanna Gutierrez |  | Miami Charter Manager |  |
| Mishka Ahmad |  | Security Manager |  |
| Fatima Sabir |  | Lawyer |  |
| 3. Stakeholders - New |  |  |  |
| Name |  |  | Department |
| List at least 3 internal or and 1 external stakeholder (i.e. vendor) |  |  | Department |
| Javier Quiñones |  |  | Ikea Manager US |
| Farzana Imran |  |  | Customer |
| Catalina Suarez |  |  | VP of SLSP |
| John Suarez |  |  | CEO of SLSP |
| Julie Tapia |  |  | VP of Operations |
| 4. Project Objectives – Update if necessary |  |  |  |  |
| By expanding operations into Florida SLSP will be able to attract more donations from individuals living in the region and expand operations into a new territory. This expansion will in turn solidify the name of the company and grant the recognition needed to obtain bigger donations from the government and other organizations. The main objective of the project is to have a functioning housing facility by the end of November 2021. So that it can be occupied with victims by December 2021. High level requirements include 15 rooms, 5 bathrooms, 3 kitchens. Be wheelchair accessible and comply with housing regulations. |  |  |  |  |
| 5. Project Milestones - New |  |  |  |  |
| - Having a catalogue with at least 5 properties that qualify for purchase. - Interviewing 5 qualified candidates for each position. - Offering a proposal of purchase. - Signing contracts and finalizing purchase of building. - Assembling team of volunteers. - Fixing possible issues of building (renovating) - Finishing Clean up and Furnishing of facility. - Pass safety inspections. - Hiring onsite team. |  |  |  |  |
| 6. High-Level Budget - Update if necessary |  |  |  |  |
| Building: $1,100,000.00 (Building purchase $950,000.00, modifications, repairs, renovations $150,000.00) Furniture: $200,000.00 ($10,000.00 per room, $10,000.00 per kitchen, $2,500.00 per bathroom, $7,500.00 office) Staffing: $200,000.00 (includes salaries of Project Team, additional staff for moving, specialized cleaning, and food, water, special clothing for volunteers) |  |  |  |  |
| 7. Assumptions and Constraints - Update if necessary |  |  |  |  |
| Assumptions: Covid is coming to an end and will be under control by the end of 2021, making it possible for victims of domestic abuse to seek alternative forms of housing and for people to work on normal circumstances. Housing prices are stable (hopefully low) and not on the rise. Most of the volunteers will be vaccinated and willing to wear masks while working. Volunteers will supply most of the labor for activities like moving and assembling furniture, cleaning the building, painting, decorating, and organizing. Additional staff will be hired for things like repairs, renovations, deep cleaning, inspections, heavy objects moving. Constrains: The budget of the project is significantly tight for the building cost. The project relies heavily on volunteers which can be unreliable. The furniture will be provided by Ikea and needs to be moved to the building; a moving company will need to be hired. Building needs to pass inspection before it´s open to the victims, which can be affected by the course of the pandemic. |  |  |  |  |
| 8. High-Level Risks - New |  |  |  |  |
| List any conditions that may limit the project team’s options with respect to resources, personnel, or schedule (e.g., predetermined budget or project end date, limit on number of staff that may be assigned to the project). - The housing market is booming at the moment and the price point of properties is significantly higher than at the beginning of the project. The housing market is floded with buyers and this lowers the probability of our offer being accepted. These two risks could increase the budget of the project and also delay the end date of it. - Huricane season is something that the Project Manager did not plan for it as she is new to Miami. A disaster recovery plan that includes inclement weather protection (shields, generator, water pumps) must be included in the budget. - Protests against police brutality have returned following more incidents of police brutality. If protests were to occur in Miami, specifically in the neighbordhoods where we are seeking to purchase a property, there is a risk of potential damage to our property. It is essential to add to the budget an insurance policy that includes protection from these incidents. |  |  |  |  |