Section 5 Assignment - Monitoring and Controlling

1. Monitor and Control Project Work:

Refer to 4.5 Monitor and Control Project Work in the Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) - Sixth Edition, Project Management Institute, Inc., 2017, Pages 105-113.

Monitoring and controlling a project from start to finish is one of the most crucial tasks for a project manager.  As you review the knowledge areas in the PMBOK® Guide, you will notice that this process is present in almost every knowledge area.  In the following table, list three important tasks you would need to perform to ensure that your stakeholders understand the current status of your project and the steps you would need to take to ensure the project deliverables are on target.  Delete the example after inputting your content.

| No. | Task | Rationale |
| --- | --- | --- |
| 1 | i.e. Hold weekly meetings | To facilitate communication among all team members so that they can provide their status, share experiences, offer suggestions, raise concerns, and resolve problems. |
| 2 | List of issues and Ideas | I’d have a drive with an anonymous document where people can write any issues that come up or ideas that might facilitate work. This would get discussed in the meetings. |
| 3 | Monthly Report | In this document I would get input from all the members of the team and once is drafted it would be sent to everybody so that the whole team is aware of the issues solved and the state of the project. |
| 4 | KPI’s and Rock Goals | Each member of the project team would have goals that are related to the progress of the project and their completion would be tied to a specific deliverable/project phase. By tracking the team members’ performance, I could also see the progress of the project. |

PMBOK is a registered mark of the Project Management Institute, Inc.

2. Validate Project Scope: 
Refer to 5.5 Validate Scope in the PMBOK® Guide, Pages 163-167.  
Assume deliverables have been met, and list those deliverables here.

Deliverables that have been met

- A building was found that meets 87% of the requirements and it was purchased in April. The only requirements that were not met were the parking spaces needed, and the closeness to Downtown. - We managed to assemble a team of 10 volunteers that were available to work and adjust to our schedule. - The Building needed minimal repair work and it will be ready to be open within 3 months of purchase, on schedule. - Even with the repairs included, the project stayed in budget. - The volunteers cleaned the building and helped installed the donated furniture by Ikea. - The inspections were all passed with flying colors. - The onsite team was hired and has started working on contacting women to start the move in process in November.

PMBOK is a registered mark of the Project Management Institute, Inc.

3. Change Requests:

Refer to 4.5.3.2 Monitor and Control Project Work: Outputs in the PMBOK® Guide, Pages 112-113 and 4.3.3.4 Change Request on Page 96.

Analysis of project performance and interactions often generates change requests.  Assume that a communication with the stakeholders resulted in a change request to add a new deliverable to the scope of the project.  Delineate the nature of that communication (hypothetically), the key points, and the change that was prompted by the communication.  Enter the change request information in the following template:

Project Change Request Form

| Project Name: | SLSP Miami Charter |
| --- | --- |
| Date: | 05/10/21 |
| Change Number | 03 |

| Request Details: |  |
| --- | --- |
| Originator Name: | Brendon Teles |
| Describe the Proposed Change: | A room must be designated as a child area. This room can include children’s toys, small library, a place to do homework, and a TV. This would provide a place for kids to be while their mothers are working from home or at the office. |
| Reasons for the Desired Change: | It would make the building more family friendly and it would provide a space for kids to bond and allow the mothers to work in peace. |
| Anticipated Impact (Quantitative): | An additional $4,000 dollars will be needed to furnish this room. |
| Desired Outcome (Qualitative): | A place where kids can play and do homework after class without disturbing their mothers if they happened to be working. This would in turn help mothers stay productive and keep their jobs. |
| Evaluation |  |
| Receiver Name | Sara Suarez |
| Potential Change Synopsis | A room that was previously designed to be a bedroom would have to be changed to a children’s room. Additional furniture will have to be negotiated with Ikea and this would have to be advertised in the website of SLSP as is only going to be offered at the Miami location. |
| Estimated Impact (Quantitative) | This will add 3 more days of communications with Ikea to formalize the change. An additional 2 days of work will also have to be added as volunteers will need to be called again to assemble the furniture required for this room. |
| Decision |  |
| Evaluated By: | John Suarez and Catalina Suarez |
| Approval/Rejection: | Approved |
| Cost/Time/Scope Change: | +$4,000, +5 days of work, no change in scope. |
| Comments | This will be really good for the new era of working remotely and it will help mothers that are struggling to find daycare. |

PMBOK is a registered mark of the Project Management Institute, Inc.